## Sheet1
Work item/Action item | ETA | Comments
Maintainer names should end with -MNT | By End of Q2 2021
Changed: attribute unreliable. | Requires further discussion on DBWG list
Web page for release cycles and forthcoming features and another one for issues under discussion. | By End of Q1 2021
Domain objects should be limited to minimum allocation size. | Requires further discussion on DBWG list
Resource holders without email addresses | By End of Q2 2021
Domain objects ending with a dot. | Done
Complete overhaul of the database manual | Requires further discussion on DBWG list
Upload/share the presentations | Done
Creation of Github page - Co-chairs | Done
Add the issues to be tracked - Co-chairs | By End of Q1 2021 | To be confirmed with co-chairs
Impact assessment on impact of creating multiple domain objects in one go in the DB | By End of Q1 2021
Discuss internally about providing DB schema in location where its accessible to the DBWG | By End of Q1 2021
Share the stats again of those mntner objects that exist without the -MNT on the DBWG list | First week of March 2021
Assess if there will be issues for members creating their own mntner as opposed to auto-generating it and revert back to DBWG | By End of Q1 2021